## Product Backlog
PRODUCT BACKLOG
ID/UserStory No. | User Story No. | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Search Function | us1 | 1 | 15 hours | In progress | Pass All tests. Approved by Product Owner
2 | Price Comparison | us2 | 1 | 20 hours | In progress | Pass All tests. Approved by Product Owner
3 | Checkout/Delivery | us3 | 1 | 15 hours | In progress | Pass All tests. Approved by Product Owner
4 | Price Sorting | us4 | 1 | 15 hours | In progress | Pass All tests. Approved by Product Owner
5 | Mailing List | us5 | 1 | 10 hours | In progress | Pass All tests. Approved by Product Owner
6 | Reviews | us6 | 2 | 20 hours | In progress | Pass All tests. Approved by Product Owner

## Sprint1 Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | Search Functionality | 1.1 | Design the layout for homepage to include a prominent search bar | Already Completed in previous sprints |  |  | x
|  | 1.2 | Implement the homepage using HTML and CSS | Arsa & Kalana | x
|  | 1.3 | Set up JS functions to handle user input and trigger search queries | Rishav & Ruvindu | x
|  | 1.4 | Write SQL Queries for search function | Rishav & Ruvindu | x
|  | 1.5 | Design the database to store product information | Salmaan & Daniel | x
2 | Price Comparison | 2.1 | Design the Layout for displaying items with details such as price, store etc. | Already Completed in previous sprints |  |  | x
|  | 2.2 | Implement the Item display layout using HTMl and CSS | Salmaan & Daniel | x
|  | 2.3 | set up JS functions to make requests to sort products base on price, distance etc. | Rishav & Ruvindu | x
|  | 2.4 | Write SQL queries to sort products | Arsa & Kalana | x
6 | Mailing List | 6.1 | Design UI to include newsletter prompt | Salmaan & Daniel | x
|  | 6.2 | Add JS function to save email to database | Arsa & Kalana | x

## Sprint2 Backlog
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | Checkout/Delivery | 3.1 | Design the Layout for the ordering page with delivery options | Already Completed in previous sprints |  |  | x
|  | 3.2 | Implement the ordering page and delivering option layout using HTML and CSS | Salmaan & Daniel | x
|  | 3.3 | Set up a form for users to select delivery options | Arsa & Kalana | x
|  | 3.4 | Write SQL queries to get details for different delivery options such as price, time, estimate, etc. | Salmaan & Daniel | x
|  | 4.1 | Design the layout for comparing prices for a product between different brands | Rishav & Ruvindu | x
|  | 4.2 | Implement the comparison page layout using HTMl and CSS | Arsa & Kalana | x
|  | 4.3 | Set up JS functions to sort items that are being compared to | Arsa & Kalana | x
|  | 4.5 | Write SQL queries to get items from different stores that are similar to a given item | Rishav & Ruvindu | x
5 | Reviews | 5.1 | Design a review section for the product page | Already Completed in previous sprints |  |  | x
|  | 5.2 | Setup JS functions to display reviews | Rishav & Ruvindu | x
|  | 5.3 | Write SQL queries to retrieve reviews | Salmaan & Daniel | x

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Search Functionality | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Price Comparison | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | Mailing List | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!