## Product Backlog
PRODUCT BACKLOG
ID/UserStory No. | User Story No. | PRIORITY | EFFORT (hours) | STATUS | DEFINITION OF DONE | NOTES
1 | Product Search (Search Bar) | 1 | 15 | Complete | Pass All tests. Approved by Product Owner
3 | Delivery Options | 5 | 10 | not started | Pass All tests. Approved by Product Owner
4 | Product Price Comparison | 4 | 10 | Complete | Pass All tests. Approved by Product Owner
5 | Display Reviews | 8 | 6 | In Progress | Pass All tests. Approved by Product Owner
6 | Receive Deal Notifications | 6 | 7 | not started | Pass All tests. Approved by Product Owner
7 | Leave Reviews | 7 | 8 | not started | Pass All tests. Approved by Product Owner
8 | Sign in Page | 5 | 12 | not started | Pass All tests. Approved by Product Owner
9 | Account Registration | 5 | 11 | In Progress | Pass All tests. Approved by Product Owner
10 | Remember Login | 5 | 7 | not started | Pass All tests. Approved by Product Owner
11 | Product Search (By Category) | 2 | 10 | Complete | Pass All tests. Approved by Product Owner
12 | Search Result Sorting | 3 | 6 | Complete | Pass All tests. Approved by Product Owner
13 | Search Result Filtering | 4 | 7 | Complete | Pass All tests. Approved by Product Owner
14 | Products on Special | 6 | 6 | Complete | Pass All tests. Approved by Product Owner
15 | Trending Products | 6 | 9 | not started | Pass All tests. Approved by Product Owner

## Sprint1 Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | Estimation | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | Product Search (Search Bar) | 1.1 | Design the layout for homepage to include a prominent search bar | 2 | Already Completed in previous sprints |  |  | x
|  | 1.2 | Implement the searchbar and search results using HTML and CSS | 3 | Arsa & Kalana |  |  | x
|  | 1.3 | Set up JS functions to handle user input and trigger search queries | 3 | Arsa & Kalana |  |  | x
|  | 1.4 | Write SQL Queries for search function | 3 | Rishav & Ruvindu |  |  | x
|  | 1.5 | Design the database to store product information | 3 | Salmaan & Daniel |  |  | x
|  | 1.6 | Implement tests for search result listings | 1 | Rishav & Ruvindu |  |  | x
4 | Product Price Comparison | 4.1 | Design the layout for comparing prices for a product between different brands | 2 | Already Completed in previous sprints |  |  | x
|  | 4.2 | Implement the comparison page layout using HTML and CSS | 3 | Salmaan & Daniel |  |  | x
|  | 4.3 | Set up JS functions to sort items that are being compared | 2 | Arsa & Kalana |  |  | x
|  | 4.4 | Write SQL queries to get items from different stores that are similar to a given item | 2 | Salmaan & Daniel |  |  | x
|  | 4.5 | Implement tests for similar item retreival | 1 | Rishav & Ruvindu |  |  | x
11 | Product Search (By Category) | 11.1 | Design the Homepage to display categories to select | 1 | Already Completed in previous sprints |  |  | x
|  | 11.2 | Implement category display on homepage | 3 | Arsa & Kalana |  |  | x
|  | 11.3 | Connect front end with backend api | 3 | Arsa & Kalana |  |  | x
|  | 11.4 | Write sql queries for retrieving categories | 2 | Rishav & Ruvindu |  |  | x
|  | 11.5 | Implement tests for each product category | 1 | Rishav & Ruvindu |  |  | x
12 | Search Result Sorting | 12.1 | Implement Search Result Sorting Selection on Front End | 1 | Arsa & Kalana |  |  | x
|  | 12.2 | Write sql queries to sort results by selected sort function | 1 | Salmaan & Daniel |  |  | x
|  | 12.3 | Connect front end with backend api | 3 | Rishav & Ruvindu |  |  | x
|  | 12.4 | Implement Tests for each sorting type | 1 | Rishav & Ruvindu |  |  | x
13 | Search Result Filtering | 13.1 | Implement Search Result Filtering Selection on Front End | 1 | Arsa & Kalana |  |  | x
|  | 13.2 | Write SQL queries to sort results by selected Filter Function | 1 | Salmaan & Daniel |  |  | x
|  | 13.3 | Connect Front end with backend api | 3 | Rishav & Ruvindu |  |  | x
|  | 13.4 | Implement tests for each filter option | 2 |  |  |  | x
8 | Sign in Page | 8.1 | Design the Sign in Page | 1 | Already Completed in previous sprints |  |  | x
|  | 8.2 | Implement the sign in page on front end | 3 | Arsa & Kalana |  |  | x
|  | 8.3 | Connect front end with back end api to confirm/allow login | 3 | Salmaan & Daniel |  |  | x
|  | 8.4 | Create API methods to allow account login | 4 | Salmaan & Daniel |  |  | x
|  | 8.5 | Implement tests for sign in validation | 1 | Rishav & Ruvindu |  |  | x

## Sprint2 Backlog
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | Estimation | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | Delivery Options | 3.1 | Design the Layout for the ordering page with delivery options | 2 | Already Completed in previous sprints |  |  | x
|  | 3.2 | Implement the ordering page and delivering option layout using HTML and CSS | 3 | Salmaan & Daniel | x
|  | 3.3 | Set up a form for users to select delivery options | 1 | Arsa & Kalana | x
|  | 3.4 | Write SQL queries to get details for different delivery options such as price, time, estimate, etc. | 3 | Salmaan & Daniel | x
|  | 3.5 | Implement tests for delivery option retrieval | 1 | Rishav & Ruvindu | x
5 | Display Reviews | 5.1 | Design a review section for the product page | 1 | Already Completed in previous sprints |  |  | x
|  | 5.2 | Setup JS functions to display reviews | 2 | Rishav & Ruvindu |  | x
|  | 5.3 | Write SQL queries to retrieve reviews | 2 | Salmaan & Daniel |  |  | x
|  | 5.4 | Implement tests for review retrieval | 1 | Salmaan & Daniel |  |  | x
6 | Receive Deal Notifications | 6.1 | Design UI to include newsletter prompt | 1 | Already Completed in previous sprints |  |  | x
|  | 6.2 | Implement the newsletter prompt in front end | 2 | Arsa & Kalana | x
|  | 6.3 | Add JS functions to save an input email to the database | 3 | Arsa & Kalana | x
|  | 6.4 | Implement tests for saving input email | 1 | Rishav & Ruvindu | x
7 | Leave Reviews | 7.1 | Design a leave review form on the product page | 1 | Already Completed in previous sprints |  |  | x
|  | 7.2 | Implement the review form in front end | 2 | Arsa & Kalana | x
|  | 7.3 | Set up JS functions to save user reviews | 2 | Salmaan & Daniel | x
|  | 7.4 | Write SQL queries to save reviews | 2 | Arsa & Kalana | x
|  | 7.5 | Implement tests for successful review creation in database | 1 | Rishav & Ruvindu | x
9 | Account Registration | 9.1 | Design the account registration page | 1 | Already Completed in previous sprints |  |  | x
|  | 9.2 | implement the registration page on front end | 3 | Arsa & Kalana |  |  | x
|  | 9.3 | Create API method to allow for account creation | 3 | Salmaan & Daniel |  |  | x
|  | 9.4 | Connect front end with back end api to create account | 3 | Arsa & Kalana | x
|  | 9.5 | Implement tests for account creation | 1 | Rishav & Ruvindu | x
10 | Remember Login | 10.1 | Implement the remember login checkbox on front end | 1 | Arsa & Kalana | x
|  | 10.2 | Create method in backend to create authorisation token | 3 | Rishav & Ruvindu | x
|  | 10.3 | Connect front end with backend to allow for login remembering | 2 | Salmaan & Daniel | x
|  | 10.4 | Implement tests for login token validation | 1 | Rishav & Ruvindu | x
14 | Products on Special | 14.1 | Implement "Special" Tab and Row on Front end Homepage | 1 | Arsa & Kalana |  |  | x
|  | 14.2 | Write sql queries to retrieve products on special | 1 | Salmaan & Daniel |  |  | x
|  | 14.3 | Connnect front end with back end api | 3 | Rishav & Ruvindu | x
|  | 14.4 | Implement tests for retreiving products on special | 1 | Rishav & Ruvindu |  |  | x
15 | Trending Products | 15.1 | Implement "Trending" Tab and Row on Front End Homepage | 1 | Arsa & Kalana | x
|  | 15.2 | Write SQL queries to retrieve products which have been purchased the most | 3 | Salmaan & Daniel | x
|  | 15.3 | Connect front end with backend api | 3 | Salmaan & Daniel | x
|  | 15.4 | Implement tests for trending product calculations | 2 | Rishav & Ruvindu | x

## burndown charts
Effort in Hours
Sprint 1 | [5 empty] | Sprint 2 | TBD |  |  |  |  | Total (Sprint 1&2) |  | TBD
Week | Planned | Actual | Actual. Rem. | Ideal rem. | Ideal per wk | Week | Planned | Actual | Actual. Rem. | Ideal Rem. | Ideal per wk | Week | Planned | Actual | Actual. Rem. | Ideal Rem. | Ideal per wk
0 | 0 | 0 | 60 | 60 |  | 0 | 0 | 0 | 64 | 64 |  | 0 | 0 | 0 | 124 | 124
1 | 22 | 25 | 35 | 40 | 20 | 1 | 24 |  |  | 42.6667 | 21.3333 | 1 | 22 | 25 | 99 | 103.3333 | 20.6667
2 | 18 | 27 | 8 | 20 | 20 | 2 | 22 |  |  | 21.3333 | 21.3333 | 2 | 18 | 27 | 72 | 82.6667 | 20.6667
3 | 20 | 29 | -21 | 0 | 20 | 3 | 18 |  |  | 0 | 21.3333 | 3 | 20 | 29 | 43 | 62 | 20.6667
total | 60 | 81 |  |  |  | total | 64 | 0 |  |  |  | 4 | 24 |  |  | 41.3333 | 20.6667
[12 empty] | 5 | 22 |  |  | 20.6667 | 20.6667
[12 empty] | 6 | 18 |  |  | 0 | 20.6667
[12 empty] | total | 124 | 81
0

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Product Search (Search Bar) | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | Receive Deal Notifications | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!